## Sheet2
Progress Report GICUMBI DISTRICT: Rukomo Sector (From 1st September to 15th September 2026)
S/N | Creator Name | User Name | Surveyed LV Line Records(km)
1 | Ngurinzira J.D'Amour | jeandamourngurinzira22 | 1.9467
2 | Manzi Intime | maniraguhatheogene01 | 4.8402
3 | BIZIMANA Jean de Dieu | nambajimana281 | 7.074
4 | Nshimiyimana Jean Baptiste | ninamenye9683 | 7.1
Total

## Transformer Tracking Log
Transformer Boundary Continuation Log - Progress Report GICUMBI DISTRICT: Rukomo Sector (From 1st September to 15th September 2026)
The selected boundary localizes distribution transformers first. Matching surveyor LV lines are then followed beyond the boundary; those extension records are included in the main report totals and itemized below.
Transformers |  | Surveyors | 4 | LV records |  | LV km |  | Cross / outside |  | Exception km
Warnings | 25 | Selected boundary: Gicumbi / Rukomo
Localized Transformer Register
Transformer No. | Transformer Name | System OBJECTID(s) | Surveyor(s) Working | LV Records | Total km | Crossing Records | Outside Records | Exception km
T-001 | Cyuru2 | 250617 | Manzi Intime (maniraguhatheogene01) | 16 | 1.5624 | 0 | 0 | 0
T-002 | Gahumuliza | 239417 | Ngurinzira J.D'Amour (jeandamourngurinzira22) | 9 | 1.9467 | 2 | 6 | 1.9209
T-003 | Mburamazi trf | 227017 | Manzi Intime (maniraguhatheogene01) | 29 | 3.2171 | 0 | 0 | 0
T-004 | Munyinya 1 | 251017 | BIZIMANA Jean de Dieu (nambajimana281) | 5 | 0.79061 | 0 | 0 | 0
T-005 | Munyinya 2 | 255021 | BIZIMANA Jean de Dieu (nambajimana281) | 7 | 1.622 | 0 | 0 | 0
T-006 | Nyinawimana | 255822 | Manzi Intime (maniraguhatheogene01) | 2 | 0.060608 | 1 | 1 | 0.060608
T-007 | Rukomo/Meshero | 226217 | BIZIMANA Jean de Dieu (nambajimana281) | 28 | 4.6613 | 0 | 0 | 0
T-008 | Ryarubanza | 240217 | Nshimiyimana Jean Baptiste (ninamenye9683) | 36 | 7.1 | 0 | 0 | 0
Boundary Continuation Detail
S/N | Transformer No. | Transformer Name | Transformer OBJECTID(s) | Creator Name | User Name | Line OBJECTID | Boundary Status | Line km | District(s) Touched | Sector(s) Touched | Cell(s) Touched | Created Date
1 | T-002 | Gahumuliza | 239417 | Ngurinzira J.D'Amour | jeandamourngurinzira22 | 578982 | CROSSES SELECTED BOUNDARY | 0.14082 | Gicumbi | Nyamiyaga; Rukomo | Cyuru; Gahumuliza; Kabeza | 2026-09-14 12:29
2 | T-002 | Gahumuliza | 239417 | Ngurinzira J.D'Amour | jeandamourngurinzira22 | 593780 | CROSSES SELECTED BOUNDARY | 0.04262 | Gicumbi | Nyamiyaga; Rukomo | Cyuru; Kabeza | 2026-09-14 12:44
3 | T-002 | Gahumuliza | 239417 | Ngurinzira J.D'Amour | jeandamourngurinzira22 | 572182 | FOLLOWED OUTSIDE BOUNDARY | 0.23183 | Gicumbi | Nyamiyaga | Kabeza | 2026-09-14 12:38
4 | T-002 | Gahumuliza | 239417 | Ngurinzira J.D'Amour | jeandamourngurinzira22 | 602981 | FOLLOWED OUTSIDE BOUNDARY | 0.63241 | Gicumbi | Nyamiyaga | Kabeza; Mataba | 2026-09-14 13:13
5 | T-002 | Gahumuliza | 239417 | Ngurinzira J.D'Amour | jeandamourngurinzira22 | 624181 | FOLLOWED OUTSIDE BOUNDARY | 0.49998 | Gicumbi | Nyamiyaga | Mataba | 2026-09-14 13:39
6 | T-002 | Gahumuliza | 239417 | Ngurinzira J.D'Amour | jeandamourngurinzira22 | 631780 | FOLLOWED OUTSIDE BOUNDARY | 0.099293 | Gicumbi | Nyamiyaga | Mataba | 2026-09-14 13:50
7 | T-002 | Gahumuliza | 239417 | Ngurinzira J.D'Amour | jeandamourngurinzira22 | 632181 | FOLLOWED OUTSIDE BOUNDARY | 0.11122 | Gicumbi | Nyamiyaga | Mataba | 2026-09-14 13:55
8 | T-002 | Gahumuliza | 239417 | Ngurinzira J.D'Amour | jeandamourngurinzira22 | 636582 | FOLLOWED OUTSIDE BOUNDARY | 0.16274 | Gicumbi | Nyamiyaga | Mataba | 2026-09-14 14:03
9 | T-006 | Nyinawimana | 255822 | Manzi Intime | maniraguhatheogene01 | 713015 | CROSSES SELECTED BOUNDARY | 0.020446 | Gicumbi | Nyamiyaga; Rukomo | Cyuru; Kiziba | 2026-09-15 07:51
10 | T-006 | Nyinawimana | 255822 | Manzi Intime | maniraguhatheogene01 | 686206 | FOLLOWED OUTSIDE BOUNDARY | 0.040162 | Gicumbi | Nyamiyaga | Kiziba | 2026-09-15 07:52
Localization Warnings - In-Boundary Lines Not Counted
S/N | Line OBJECTID | Creator Name | User Name | Entered Transformer Name | Line km | Recorded Sector | Reason
1 | 612980 | Nshimiyimana Jean Baptiste | ninamenye9683 | [Blank] | 0.048806 |  | No matching distribution-transformer point was localized inside the selected boundary.
2 | 613380 | Nshimiyimana Jean Baptiste | ninamenye9683 | [Blank] | 0.048806 |  | No matching distribution-transformer point was localized inside the selected boundary.
3 | 489781 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.056786 |  | No matching distribution-transformer point was localized inside the selected boundary.
4 | 492985 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.13678 |  | No matching distribution-transformer point was localized inside the selected boundary.
5 | 494579 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.20191 |  | No matching distribution-transformer point was localized inside the selected boundary.
6 | 494980 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.17211 |  | No matching distribution-transformer point was localized inside the selected boundary.
7 | 494985 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.27521 |  | No matching distribution-transformer point was localized inside the selected boundary.
8 | 500582 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.18346 |  | No matching distribution-transformer point was localized inside the selected boundary.
9 | 500980 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.20328 |  | No matching distribution-transformer point was localized inside the selected boundary.
10 | 501379 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.10793 |  | No matching distribution-transformer point was localized inside the selected boundary.
11 | 502980 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.27202 |  | No matching distribution-transformer point was localized inside the selected boundary.
12 | 502985 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.084203 |  | No matching distribution-transformer point was localized inside the selected boundary.
13 | 506179 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.18226 |  | No matching distribution-transformer point was localized inside the selected boundary.
14 | 521379 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.2306 |  | No matching distribution-transformer point was localized inside the selected boundary.
15 | 526579 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.28501 |  | No matching distribution-transformer point was localized inside the selected boundary.
16 | 540979 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.24067 |  | No matching distribution-transformer point was localized inside the selected boundary.
17 | 542179 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.064686 |  | No matching distribution-transformer point was localized inside the selected boundary.
18 | 550179 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.19899 |  | No matching distribution-transformer point was localized inside the selected boundary.
19 | 551779 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.30942 |  | No matching distribution-transformer point was localized inside the selected boundary.
20 | 557779 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.30942 |  | No matching distribution-transformer point was localized inside the selected boundary.
21 | 568179 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.091183 |  | No matching distribution-transformer point was localized inside the selected boundary.
22 | 685805 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.077206 |  | No matching distribution-transformer point was localized inside the selected boundary.
23 | 715014 | Nshimiyimana Jean Baptiste | ninamenye9683 | Kiosque/Rukomo | 0.054972 |  | No matching distribution-transformer point was localized inside the selected boundary.
24 | 683386 | BIZIMANA Jean de Dieu | nambajimana281 | Rukomo/ Meshero | 0.22004 |  | No matching distribution-transformer point was localized inside the selected boundary.
25 | 505782 | BIZIMANA Jean de Dieu | nambajimana281 | Rukomo/Mashero | 0.27145 |  | No matching distribution-transformer point was localized inside the selected boundary.